## Hoja1
CODE | TASK |  |  | WHO? | Equipment | Efficiency |  | Amount |  | Duration
F.01 | Demolition
|  | Demolition of the existent building and debris transport |  | Subcontractor | Subcontractor |  |  |  |  | 15 days
F.02 | Previous actions
|  | Fencing and signaling the site |  | 2 ordinary pawn | ---- | 0.3 | h/m | 32.14 | m | 9.642 | h
F.03 | Gym's foundation
|  | Excavation in gym zone |  | Official and ordinary pawn in construction | Backhoe, truck | 0.01 | h/m3 | 406.33 | m3 | 4.0633 | h
|  | Excavation for gym's sewerage |  | Official and ordinary pawn in construction | Backhoe, truck | 0.06 | h/m3 | 5.22 | m3 | 0.3132 | h
|  | Gym's sewerage installation |  | 1st official and ordinary pawn in construction, 1st official in plumber | ---- | 0.15 | h/m | 58 | m | 8.7 | h
|  | Placement of lean concrete |  | 1st official and 2 ordinary pawn in construction | Mixer truck | 0.08 | h/m3 | 59.4 | m3 | 4.752 | h
|  | Placement of insulation (12 cm.) |  | 1st official and ordinary pawn in construction | ---- | 0.04 | h/m2 | 594.18 | m2 | 23.7672 | h
|  | Placement of insulation as lost formwork in borders |  | 1st official and specializated pawn in construction | ---- | 0.04 | h/m2 | 31.63 | m2 | 1.2652 | h
|  | Placement of foundation armor |  | Official and 3 ordinary armor assembler | ---- | 0.004 | h/kg | 15175.5 | kg | 60.702 | h
|  | Concrete placing/Vibration |  | 1st official and 2 ordinary pawn in construction | Mixer truck, vibrator | 0.08 | h/m3 | 202.34 | m3 | 16.1872 | h
|  | Fill the hole in borders with ground |  | 1st official and 1 ordinary pawn in construction | Backhoe | 0.02 | h/m3 | 12.8 | m3 | 0.256 | h
F.04 | Classes foundation
|  | Excavation in classes |  | Official and ordinary pawn in construction | Backhoe, truck | 0.01 | h/m3 | 241.88 | m3 | 2.4188 | h
|  | Excavation for classes sewerage |  | Official and ordinary pawn in construction | Backhoe, truck | 0.06 | h/m3 | 8.41 | m3 | 0.5046 | h
|  | Classes' sewerage installation |  | 1st official and ordinary pawn in construction, 1st official in plumber | ---- | 0.15 | h/m | 93.5 | m | 14.025 | h
|  | Placement of lean concrete |  | 1st official and 2 ordinary pawn in construction | Mixer truck | 0.08 | h/m3 | 37.12 | m3 | 2.9696 | h
|  | Placement of insulation (12 cm.) |  | 1st official and ordinary pawn in construction | ---- | 0.04 | h/m2 | 371.25 | m2 | 14.85 | h
|  | Placement of insulation as lost formwork in borders |  | 1st official and specializated pawn in construction | ---- | 0.04 | h/m2 | 25.61 | m2 | 1.0244 | h
|  | Placement of foundation armor |  | Official and ordinary armor assembler | ---- | 0.004 | h/kg | 9259.5 | kg | 37.038 | h
|  | Concrete placing/Vibration |  | Official and 3 ordinary armor assembler | Mixer truck, vibrator | 0.08 | h/m3 | 123.46 | m3 | 9.8768 | h
|  | Fill the hole in borders with ground |  | 1st official and 1 ordinary pawn in construction | Backhoe | 0.02 | h/m3 | 10.35 | m3 | 0.207 | h
F.05 | Theater building foundation
|  | Excavation in theater's place |  | Ordinary pawn in construction | Backhoe | 0.01 | h/m3 | 216.63 | m3 | 2.1663 | h
|  | Excavation for theater's sewerage |  | Ordinary pawn in construction | Backhoe | 0.06 | h/m3 | 9.14 | m3 | 0.5484 | h
|  | Theater sewerage installation |  | 1st official and ordinary pawn in construction, 1st official in plumber | ---- | 0.15 | h/m | 101.5 | m | 15.225 | h
|  | Placement of lean concrete |  | 1st official and 2 ordinary pawn in construction |  | 0.08 | h/m3 | 34.14 | m3 | 2.7312 | h
|  | Placement of insulation (12 cm.) |  | 1st official and ordinary pawn in construction | ---- | 0.04 | h/m2 | 341.37 | m2 | 13.6548 | h
|  | Placement of foundation armor |  | Official and 3 ordinary armor assembler | ---- | 0.004 | h/kg | 8635.5 | kg | 34.542 | h
|  | Concrete placing/Vibration |  | 1st official and 1 ordinary pawn in construction | Mixer truck, vibrator | 0.08 | h/m3 | 115.14 | m3 | 9.2112 | h
F.06 | Gym's structure
|  | Self erecting tower crane installation (in playground) |  | ---- | ---- | ---- |  | ----
Party walls in gym's zone
|  |  | Placement of insulation in existent walls as lost formwork | 1st official and ordinary pawn in construction | ---- | 0.04 | h/m2 | 595 | m2 | 23.8 | h
|  |  | Placement of armor | Official and 3 ordinary armor assembler | Crane | 0.004 | h/kg | 1958 | kg | 7.832 | h
|  |  | Placement of external formwork | 1st official and 5 specializated pawn in construction | Crane | 0.04 | h/m2 | 595 | m2 | 23.8 | h
|  |  | Concrete placing/Vibration | 1st official and 2 ordinary pawn in construction | Mixer truck, vibrator, crane | 0.08 | h/m3 | 178.5 | m3 | 14.28 | h
|  |  | Take away external formwork | 1st official and 5 specializated pawn in construction | Crane | 0.025 | h/m2 | 595 | m2 | 14.875 | h
Concrete pillars 1st level
|  |  | Placement of armor | Official and 3 ordinary armor assembler | Crane | 0.004 | h/kg | 288 | kg | 1.152 | h
|  |  | Placement of formwork | 1st official and 5 specializated pawn in construction | Crane | 0.04 | h/m2 | 33.6 | m2 | 1.344 | h
|  |  | Concrete placing/Vibration | 1st official and 2 ordinary pawn in construction | Mixer truck, vibrator, crane | 0.08 | h/m3 | 2.88 | m3 | 0.2304 | h
|  |  | Take away formwork | 1st official and 5 specializated pawn in construction | Crane | 0.025 | h/m2 | 33.6 | m2 | 0.84 | h
|  | Gym's dressing room's wall (concrete bricks) |  | 1st official and 3 specializated pawn in construction | ---- | 0.225 | h/m2 | 90.9 | m2 | 20.4525 | h
Concrete beams
|  |  | Placement of formwork and struts | 1st official and 5 specializated pawn in construction | Crane | 0.04 | h/m2 | 88.38 | m2 | 3.5352 | h
|  |  | Placement of armor | Official and 3 ordinary armor assembler | Crane | 0.004 | h/kg | 170.7 | kg | 0.6828 | h
|  |  | Concrete placing/Vibration | 1st official and 2 ordinary pawn in construction | Mixer truck, vibrator, crane | 0.08 | h/m3 | 7.415 | m3 | 0.5932 | h
|  |  | Take away formwork | 1st official and 5 specializated pawn in construction | Crane | 0.025 | h/m2 | 88.38 | m2 | 2.2095 | h
Gym's stairs
|  |  | Placement of prefabricated stairs' slabs with struts | Official, an especializated pawn and an ordinary pawn in construction | Crane | 0.17 | h/m2 | 6.3 | m2 | 1.071 | h
Concrete pillars 2nd level
|  |  | Placement of armor | Official and 3 ordinary armor assembler | Crane | 0.004 | h/kg | 540 | kg | 2.16 | h
|  |  | Placement of formwork | 1st official and 5 specializated pawn in construction | Crane | 0.04 | h/m2 | 63 | m2 | 2.52 | h
|  |  | Concrete placing/Vibration | 1st official and 2 ordinary pawn in construction | Mixer truck, vibrator, crane | 0.08 | h/m3 | 5.4 | m3 | 0.432 | h
|  |  | Take away formwork | 1st official and 5 specializated pawn in construction | Crane | 0.025 | h/m2 | 63 | m2 | 1.575 | h
F.07 | Vertical elements
Concrete pillars in theater
|  |  | Placement of armor | Official and 3 ordinary armor assembler | Crane | 0.004 | h/kg | 154 | kg | 0.616 | h
|  |  | Placement of formwork | 1st official and 5 specializated pawn in construction | Crane | 0.04 | h/m2 | 14.4 | m2 | 0.576 | h
|  |  | Concrete placing/Vibration | 1st official and 2 ordinary pawn in construction | Mixer truck, vibrator, crane | 0.08 | h/m3 | 1.54 | m3 | 0.1232 | h
|  |  | Take away formwork | 1st official and 5 specializated pawn in construction | Crane | 0.025 | h/m2 | 14.4 | m2 | 0.36 | h
Prefabricated concrete pillars in playground
|  |  | Placement of armor for foundation | Official and 3 ordinary armor assembler | Crane | 0.004 | h/kg | 90 | kg | 0.36 | h
|  |  | Placement of prefabricated pillars | 1st official and 2 specializated pawn in construction | Crane | 0.2 | h/u | 2 | u | 0.4 | h
|  |  | Concrete placing/Vibration | 1st official and 2 ordinary pawn in construction | Mixer truck, vibrator, crane | 0.08 | h/m3 | 1.2 | m3 | 0.096 | h
Party walls in classes' zone (until 1st floor)
|  |  | Placement of insulation in existent walls as lost formwork | 1st official and ordinary pawn in construction | ---- | 0.04 | h/m2 | 61.275 | m2 | 2.451 | h
|  |  | Placement of armor | Official and 3 ordinary armor assembler | Crane | 0.004 | h/kg | 134.75 | kg | 0.539 | h
|  |  | Placement of external formwork | 1st official and 5 specializated pawn in construction | Crane | 0.04 | h/m2 | 61.275 | m2 | 2.451 | h
|  |  | Concrete placing/Vibration | 1st official and 2 ordinary pawn in construction | Mixer truck, vibrator, crane | 0.08 | h/m3 | 12.25 | m3 | 0.98 | h
|  |  | Take away formwork | 1st official and 5 specializated pawn in construction | Crane | 0.025 | h/m2 | 16.275 | m2 | 0.40687 | h
Party walls in theater's zone (until 2nd floor)
|  |  | Placement of insulation in existent walls as lost formwork | 1st official and ordinary pawn in construction | ---- | 0.04 | h/m2 | 168.09 | m2 | 6.7236 | h
|  |  | Placement of armor | Official and 3 ordinary armor assembler | Crane | 0.004 | h/kg | 297.69 | kg | 1.1908 | h
|  |  | Placement of external formwork | 1st official and 5 specializated pawn in construction | Crane | 0.04 | h/m2 | 168.09 | m2 | 6.7236 | h
|  |  | Concrete placing/Vibration | 1st official and 2 ordinary pawn in construction | Mixer truck, vibrator, crane | 0.08 | h/m3 | 33.618 | m3 | 2.6894 | h
|  |  | Take away formwork | 1st official and 5 specializated pawn in construction | Crane | 0.025 | h/m2 | 168.09 | m2 | 4.2023 | h
|  | Brick walls in classes |  | 1st official and 3 specializated pawn in construction | ---- | 0.225 | h/m2 | 305.9 | m2 | 68.8275 | h
Concrete walls in theater Zone 7-8
|  |  | Placement of armor | Official and 3 ordinary armor assembler | Crane | 0.004 | h/kg | 2438.67 | kg | 9.7547 | h
|  |  | Placement of formwork | 1st official and 5 specializated pawn in construction | Crane | 0.04 | h/m2 | 270.63 | m2 | 10.8252 | h
|  |  | Concrete placing/Vibration | 1st official and 2 ordinary pawn in construction | Mixer truck, vibrator, crane | 0.08 | h/m3 | 27.063 | m3 | 2.165 | h
|  |  | Take away formwork | 1st official and 5 specializated pawn in construction | Crane | 0.025 | h/m2 | 270.63 | m2 | 6.7658 | h
Concrete walls in theater Zone 10-11
|  |  | Placement of armor | Official and 3 ordinary armor assembler | Crane | 0.004 | h/kg | 3134.7 | kg | 12.5388 | h
|  |  | Placement of formwork | 1st official and 5 specializated pawn in construction | Crane | 0.04 | h/m2 | 310.31 | m2 | 12.4124 | h
|  |  | Concrete placing/Vibration | 1st official and 2 ordinary pawn in construction | Mixer truck, vibrator, crane | 0.08 | h/m3 | 34.83 | m3 | 2.7864 | h
|  |  | Take away formwork | 1st official and 5 specializated pawn in construction | Crane | 0.025 | h/m2 | 310.31 | m2 | 7.7578 | h
|  | Brick wall in theater's groundfloor |  | 1st official and 3 specializated pawn in construction | ---- | 0.225 | h/m2 | 20.77 | m2 | 4.6733 | h
Theater's concrete beam
|  |  | Placement of formwork and struts | 1st official and 5 specializated pawn in construction | Crane | 0.04 | h/m2 | 39.19 | m2 | 1.5676 | h
|  |  | Placement of armor | Official and 3 ordinary armor assembler | Crane | 0.004 | h/kg | 410.4 | kg | 1.6416 | h
|  |  | Concrete placing/Vibration | 1st official and 2 ordinary pawn in construction | Mixer truck, vibrator, crane | 0.08 | h/m3 | 5.98 | m3 | 0.4784 | h
|  |  | Take away formwork | 1st official and 5 specializated pawn in construction | Crane | 0.025 | h/m2 | 39.19 | m2 | 0.97975 | h
|  | Brick walls between gym pillars in 2nd level |  | 1st official and 3 specializated pawn in construction | Manlift | 0.225 | h/m2 | 137.7 | m2 | 30.9825 | h
Elevator stairs (until 1st floor)
|  |  | Placement of formwork and struts | 1st official and 5 specializated pawn in construction | Crane | 0.04 | h/m2 | 8.84 | m2 | 0.3536 | h
|  |  | Placement of armor | Official and 3 ordinary armor assembler | Crane | 0.004 | h/kg | 95.76 | kg | 0.38304 | h
|  |  | Concrete placing/Vibration | 1st official and 2 ordinary pawn in construction | Mixer truck, vibrator, crane | 0.08 | h/m3 | 1.77 | m3 | 0.1416 | h
|  |  | Take away formwork | 1st official and 5 specializated pawn in construction | Crane | 0.025 | h/m2 | 8.84 | m2 | 0.221 | h
|  |  | Steps construction | 1st official and 2 ordinary pawn in construction |  | 0.72 | h/m2 | 6.84 | m2 | 4.9248 | h
F.08 | Horizontal elements
1st floor in gym
|  |  | Placement of formwork and struts | 1st official and 5 specializated pawn in construction | Crane | 0.04 | h/m2 | 133.31 | m2 | 5.3324 | h
|  |  | Placement of armor | Official and 3 ordinary armor assembler | Crane | 0.004 | h/kg | 1066.48 | kg | 4.2659 | h
|  |  | Concrete placing/Vibration | 1st official and 2 ordinary pawn in construction | Mixer truck, vibrator, crane | 0.08 | h/m3 | 26.662 | m3 | 2.133 | h
|  |  | Take away formwork | 1st official and 5 specializated pawn in construction | Crane | 0.025 | h/m2 | 133.31 | m2 | 3.3328 | h
Gym's roof
|  |  | Placement of gym's metallic beams | 1st official and 2 specialist in iron | Crane | 3.53 | h/u | 4 | u | 14.12 | h
|  |  | Gym's roof metallic elements placement | 1st official and 2 specialist in iron | Crane | 0.025 | h/m2 | 459.025 | m2 | 11.4756 | h
Classes roof (except 2, for tower crane disassembly)
|  |  | Placement of prefabricated slabs and struts | 1st official and 3 specializated pawn in construction | Crane | 0.15 | h/m2 | 213.28 | m2 | 31.992 | h
|  |  | Placement of armor | Official and 2 ordinary armor assembler | Crane | 0.004 | h/kg | 2346.08 | kg | 9.3843 | h
|  |  | Placement of concrete in slab joints | 1st official and specializated pawn in construction | Mixer truck, vibrator, crane | 0.08 | h/m3 | 2.85 | m3 | 0.228 | h
Theater's 1st floor
|  |  | Placement of formwork and struts | 1st official and 5 specializated pawn in construction | Crane | 0.04 | h/m2 | 164.34 | m2 | 6.5736 | h
|  |  | Placement of armor | Official and 3 ordinary armor assembler | Crane | 0.004 | h/kg | 2793.78 | kg | 11.1751 | h
|  |  | Concrete placing/Vibration | 1st official and 2 ordinary pawn in construction | Mixer truck, vibrator, crane | 0.08 | h/m3 | 49.302 | m3 | 3.9442 | h
|  |  | Take away formwork | 1st official and 5 specializated pawn in construction | Crane | 0.025 | h/m2 | 164.34 | m2 | 4.1085 | h
F.09 | Theater vertical elements (1st floor)
Concrete walls zone 7-8
|  |  | Scaffold installation | 1st official and specializated pawn in construction | Crane | 0.3 | h/u | 15 | u | 4.5 | h
|  |  | Inside formwork's placement | 1st official and 5 specializated pawn in construction | Crane | 0.04 | h/m2 | 102.48 | m2 | 4.0992 | h
|  |  | Placement of armor | Official and 3 ordinary armor assembler | Crane | 0.004 | h/kg | 1844.64 | kg | 7.3786 | h
|  |  | Outside formwork's placement | 1st official and 5 specializated pawn in construction | Crane | 0.04 | h/m2 | 102.48 | m2 | 4.0992 | h
|  |  | Concrete placing/Vibration | 1st official and 2 ordinary pawn in construction | Mixer truck, vibrator, crane | 0.08 | h/m3 | 20.496 | m3 | 1.6397 | h
|  |  | Take away formwork | 1st official and 5 specializated pawn in construction | Crane | 0.025 | h/m2 | 204.96 | m2 | 5.124 | h
Concrete walls zone 10-11
|  |  | Scaffold installation | 1st official and specializated pawn in construction | Crane | 0.3 | h/u | 20 | u | 6 | h
|  |  | Inside formwork's placement | 1st official and 5 specializated pawn in construction | Crane | 0.04 | h/m2 | 140.14 | m2 | 5.6056 | h
|  |  | Placement of armor | Official and 3 ordinary armor assembler | Crane | 0.004 | h/kg | 2522.52 | kg | 10.0901 | h
|  |  | Outside formwork's placement | 1st official and 5 specializated pawn in construction | Crane | 0.04 | h/m2 | 140.14 | m2 | 5.6056 | h
|  |  | Concrete placing/Vibration | 1st official and 2 ordinary pawn in construction | Mixer truck, vibrator, crane | 0.08 | h/m3 | 28.028 | m3 | 2.2422 | h
|  |  | Take away formwork | 1st official and 5 specializated pawn in construction | Crane | 0.025 | h/m2 | 280.28 | m2 | 7.007 | h
Party walls in theater's zone (until roof)
|  |  | Placement of insulation in existent walls as lost formwork | 1st official and ordinary pawn in construction | ---- | 0.04 | h/m2 | 211.2 | m2 | 8.448 | h
|  |  | Placement of armor | Official and 3 ordinary armor assembler | Crane | 0.004 | h/kg | 464.64 | kg | 1.8586 | h
|  |  | Placement of external formwork | 1st official and 5 specializated pawn in construction | Crane | 0.04 | h/m2 | 211.2 | m2 | 8.448 | h
|  |  | Concrete placing/Vibration | 1st official and 2 ordinary pawn in construction | Mixer truck, vibrator, crane | 0.08 | h/m3 | 42.24 | m3 | 3.3792 | h
|  |  | Take away formwork | 1st official and 5 specializated pawn in construction |  | 0.025 | h/m2 | 211.2 | m2 | 5.28 | h
F.10 | Theater horizontal elements (1st to 2nd floor)
Podium level
|  |  | Placement of formwork and struts | 1st official and 5 specializated pawn in construction | Crane | 0.04 | h/m2 | 142.79 | m2 | 5.7116 | h
|  |  | Placement of armor | Official and 3 ordinary armor assembler | Crane | 0.004 | h/kg | 3141.38 | kg | 12.5655 | h
|  |  | Concrete placing/Vibration | 1st official and 2 ordinary pawn in construction | Mixer truck, vibrator, crane | 0.08 | h/m3 | 35.6975 | m3 | 2.8558 | h
|  |  | Take away formwork | 1st official and 5 specializated pawn in construction | Crane | 0.025 | h/m2 | 142.79 | m2 | 3.5697 | h
Technical room floor (over WC)
|  |  | Placement of formwork and struts | 1st official and 5 specializated pawn in construction | Crane | 0.04 | h/m2 | 55.8 | m2 | 2.232 | h
|  |  | Placement of armor | Official and 3 ordinary armor assembler | Crane | 0.004 | h/kg | 446.4 | kg | 1.7856 | h
|  |  | Concrete placing/Vibration | 1st official and 2 ordinary pawn in construction | Mixer truck, vibrator, crane | 0.08 | h/m3 | 11.16 | m3 | 0.8928 | h
|  |  | Take away formwork | 1st official and 5 specializated pawn in construction | Crane | 0.025 | h/m2 | 55.8 | m2 | 1.395 | h
Elevator stairs (until 2nd floor)
|  |  | Placement of armor | Official and 3 ordinary armor assembler | Crane | 0.004 | h/kg | 95.76 | kg | 0.38304 | h
|  |  | Placement of formwork and struts | 1st official and 5 specializated pawn in construction | Crane | 0.04 | h/m2 | 8.84 | m2 | 0.3536 | h
|  |  | Concrete placing/Vibration | 1st official and 2 ordinary pawn in construction | Mixer truck, vibrator, crane | 0.08 | h/m3 | 1.77 | m3 | 0.1416 | h
|  |  | Take away formwork | 1st official and 5 specializated pawn in construction | Crane | 0.025 | h/m2 | 8.84 | m2 | 0.221 | h
|  |  | Steps construction | 1st official and 2 ordinary pawn in construction |  | 0.72 | h/m2 | 6.84 | m2 | 4.9248 | h
F.11 | Theater vertical elements (2nd floor)
Concrete walls zone 7-8
|  |  | Scaffold installation | 1st official and specializated pawn in construction | Crane | 0.3 | h/u | 15 | u | 4.5 | h
|  |  | Placement of formwork | 1st official and 5 specializated pawn in construction | Crane | 0.04 | h/m2 | 136.05 | m2 | 5.442 | h
|  |  | Placement of armor | Official and 3 ordinary armor assembler | Crane | 0.004 | h/kg | 3672.81 | kg | 14.6912 | h
|  |  | Concrete placing/Vibration | 1st official and 2 ordinary pawn in construction | Mixer truck, vibrator, crane | 0.08 | h/m3 | 40.81 | m3 | 3.2648 | h
|  |  | Take away formwork | 1st official and 5 specializated pawn in construction | Crane | 0.025 | h/m2 | 136.05 | m2 | 3.4013 | h
Concrete walls in elevator shaft
|  |  | Placement of armor | Official and 3 ordinary armor assembler | Crane | 0.004 | h/kg | 805.5 | kg | 3.222 | h
|  |  | Placement of formwork | 1st official and 5 specializated pawn in construction | Crane | 0.04 | h/m2 | 89.5 | m2 | 3.58 | h
|  |  | Concrete placing/Vibration | 1st official and 2 ordinary pawn in construction | Mixer truck, vibrator, crane | 0.08 | h/m3 | 8.95 | m3 | 0.716 | h
|  |  | Take away formwork | 1st official and 5 specializated pawn in construction | Crane | 0.025 | h/m2 | 89.5 | m2 | 2.2375 | h
Engine room floor
|  |  | Placement of formwork and struts | 1st official and 5 specializated pawn in construction | Crane | 0.04 | h/m2 | 14.8 | m2 | 0.592 | h
|  |  | Placement of armor | Official and 3 ordinary armor assembler | Crane | 0.004 | h/kg | 325.6 | kg | 1.3024 | h
|  |  | Concrete placing/Vibration | 1st official and 2 ordinary pawn in construction | Mixer truck, vibrator, crane | 0.08 | h/m3 | 2.96 | m3 | 0.2368 | h
|  |  | Take away formwork | 1st official and 5 specializated pawn in construction | Crane | 0.025 | h/m2 | 14.8 | m2 | 0.37 | h
Elevator stairs (until engine room)
|  |  | Placement of armor | Official and 3 ordinary armor assembler | Crane | 0.004 | h/kg | 95.76 | kg | 0.38304 | h
|  |  | Placement of formwork and struts | 1st official and 5 specializated pawn in construction | Crane | 0.04 | h/m2 | 8.84 | m2 | 0.3536 | h
|  |  | Concrete placing/Vibration | 1st official and 2 ordinary pawn in construction | Mixer truck, vibrator, crane | 0.08 | h/m3 | 1.77 | m3 | 0.1416 | h
|  |  | Take away formwork | 1st official and 5 specializated pawn in construction | Crane | 0.025 | h/m2 | 8.84 | m2 | 0.221 | h
|  |  | Steps construction | 1st official and 2 ordinary pawn in construction |  | 0.72 | h/m2 | 6.84 | m2 | 4.9248 | h
|  | Move crane to the street |  | Subcontractor
F.12 | Classes' elements
Classes roof in class 2
|  |  | Placement of prefabricated slabs and struts (class 2) | 1st official and 2 specializated pawn in construction | Crane | 0.15 | h/m2 | 73.81 | m2 | 11.0715 | h
|  |  | Placement of armor (class 2) | Official and 3 ordinary armor assembler | Crane | 0.004 | h/kg | 811.81 | kg | 3.2472 | h
|  |  | Placement of concrete in slab joints (class 2) | 1st official and 2 ordinary pawn in construction | Mixer truck, vibrator, crane | 0.08 | h/m3 | 0.927 | m3 | 0.07416 | h
Perimetral concrete beam
|  |  | Placement of formwork and struts | 1st official and 5 specializated pawn in construction | Crane | 0.04 | h/m2 | 45.115 | m2 | 1.8046 | h
|  |  | Placement of armor | Official and 3 ordinary armor assembler | Crane | 0.004 | h/kg | 249.12 | kg | 0.99648 | h
|  |  | Concrete placing/Vibration | 1st official and 2 ordinary pawn in construction | Mixer truck, vibrator, crane | 0.08 | h/m3 | 3.89 | m3 | 0.3112 | h
|  |  | Take away formwork | 1st official and 5 specializated pawn in construction | Crane | 0.025 | h/m2 | 45.115 | m2 | 1.1279 | h
Stairs to terrace
|  |  | Placement of prefabricated stairs slabs with struts | 1st official and 2 specializated pawn in construction |  | 2 | h/u | 2 | u | 4 | h
Terrace construction
|  |  | Placement of vapour barrier | 1st official and 2 ordinary pawn in construction | ---- | 0.005 | h/m2 | 316.59 | m2 | 1.5829 | h
|  |  | Slope formation | 1st official and ordinary pawn in construction | Mixer truck, vibrator, crane | 0.08 | h/m3 | 29.56 | m3 | 2.3648 | h
|  |  | Placement of insulation | 1st official and 2 ordinary pawn in construction | ---- | 0.04 | h/m2 | 302.615 | m2 | 12.1046 | h
|  |  | Placement of EPDM | 1st official and 2 ordinary pawn in construction | Blowtorch | 0.01 | h/m | 316.59 | m | 3.1659 | h
|  |  | Placement of adjustable supports | 1st official and 2 ordinary pawn in construction | ---- | 0.09 | h/m2 | 302.62 | m2 | 27.2358 | h
|  |  | Placement of tiles | 1st official and 2 ordinary pawn in construction | ---- | 0.2 | h/m2 | 302.62 | m2 | 60.524 | h
F.13 | Theater elements
Elevator shaft roof
|  |  | Placement of formwork and struts | 1st official and 5 specializated pawn in construction | Crane | 0.04 | h/m2 | 36.3 | m2 | 1.452 | h
|  |  | Placement of armor | Official and 3 ordinary armor assembler | Crane | 0.004 | h/kg | 792 | kg | 3.168 | h
|  |  | Concrete placing/Vibration | 1st official and 2 ordinary pawn in construction | Mixer truck, vibrator, crane | 0.08 | h/m3 | 7.62 | m3 | 0.6096 | h
|  |  | Take away formwork | 1st official and 5 specializated pawn in construction | Crane | 0.025 | h/m2 | 36.3 | m2 | 0.9075 | h
|  |  | Placement of EPDM | 1st official and 2 ordinary pawn in construction | Blowtorch | 0.01 | h/m2 | 36.3 | m2 | 0.363 | h
|  |  | Placement of grave | 1 ordinary pawn in construction | Crane | 0.016 | h/m2 | 36.3 | m2 | 0.5808 | h
Theater wall 1st part
|  |  | Scaffold instalation | 1st official and specializated pawn in construction | Crane | 0.3 | h/u | 22 | u | 6.6 | h
|  |  | Inside formwork's placement | 1st official and 5 specializated pawn in construction | Crane | 0.04 | h/m2 | 361.83 | m2 | 14.4732 | h
|  |  | Placement of armor | Official and 3 ordinary armor assembler | Crane | 0.004 | h/kg | 9769.36 | kg | 39.0774 | h
|  |  | Outside formwork's placement | 1st official and 5 specializated pawn in construction | Crane | 0.04 | h/m2 | 361.83 | m2 | 14.4732 | h
|  |  | Concrete placing/Vibration | 1st official and 2 ordinary pawn in construction | Mixer truck, vibrator, crane | 0.08 | h/m3 | 108.55 | m3 | 8.684 | h
|  |  | Take away formwork | 1st official and 5 specializated pawn in construction | Crane | 0.025 | h/m2 | 723.64 | m2 | 18.091 | h
Theater wall 2nd part
|  |  | Scaffold instalation | 1st official and specializated pawn in construction | Crane | 0.3 | h/u | 22 | u | 6.6 | h
|  |  | Inside formwork's placement | 1st official and 5 specializated pawn in construction | Crane | 0.04 | h/m2 | 156.63 | m2 | 6.2652 | h
|  |  | Placement of armor | Official and 3 ordinary armor assembler | Crane | 0.004 | h/kg | 4229.01 | kg | 16.916 | h
|  |  | Outside formwork's placement | 1st official and 5 specializated pawn in construction | Crane | 0.04 | h/m2 | 156.63 | m2 | 6.2652 | h
|  |  | Concrete placing/Vibration | 1st official and 2 ordinary pawn in construction | Mixer truck, vibrator, crane | 0.08 | h/m3 | 46.99 | m3 | 3.7592 | h
|  |  | Take away formwork | 1st official and 5 specializated pawn in construction | Crane | 0.025 | h/m2 | 313.26 | m2 | 7.8315 | h
Theater floor
|  |  | Placement prefabricated slabs with struts | 1st official and 5 specializated pawn in construction | Crane | 0.15 | h/m2 | 198.69 | m2 | 29.8035 | h
Theater stairs
|  |  | Placement of prefabricated slabs with struts | 1st official and 5 specializated pawn in construction | Crane | 2 | h/u | 4 | u | 8 | h
Theater roof
|  |  | Placement of prefabricated slabs and struts | 1st official and 2 specializated pawn in construction | Crane | 0.15 | h/m2 | 414.43 | m2 | 62.1645 | h
|  |  | Placement of armor | Official and 3 ordinary armor assembler | Crane | 0.004 | h/kg | 4558.73 | kg | 18.2349 | h
|  |  | Placement of concrete in slab joints | 1st official and 2 ordinary pawn in construction | Mixer truck, vibrator, crane | 0.08 | h/m3 | 52.47 | m3 | 4.1976 | h
|  |  | Placement of vapour barrier | 1st official and 2 ordinary pawn in construction | ---- | 0.005 | h/m2 | 414.43 | m2 | 2.0722 | h
|  |  | Slope formation | 1st official and ordinary pawn in construction | Mixer truck, vibrator, crane | 0.08 | h/m3 | 41.44 | m3 | 3.3152 | h
|  |  | Placement of insulation | 1st official and 2 ordinary pawn in construction | ---- | 0.04 | h/m2 | 414.43 | m2 | 16.5772 | h
|  |  | Placement of EPDM | 1st official and 2 ordinary pawn in construction | Blowtorch | 0.01 | h/m2 | 414.43 | m2 | 4.1443 | h
|  |  | Placement of grave | 1 ordinary pawn in construction | Crane | 0.016 | h/m2 | 414.43 | m2 | 6.6309 | h
|  | Removal of the crane |  | ---- | ----
Glass walls
|  |  | Instalation of main structure in classes wall | Subcontractor | ----
|  |  | Instalation of main structure in theater wall | Subcontractor | ----
F.14 | Comfort installation
|  | Placement of insulation in gym |  | 1st official and ordinary pawn in construction |  | 0.04 | h/m2 | 211.97 | m2 | 8.4788 | h
|  | Placement of insulation in theater |  | 1st official and ordinary pawn in construction |  | 0.04 | h/m2 | 713.31 | m2 | 28.5324 | h
|  | Placement of insulation in classes |  | 1st official and ordinary pawn in construction |  | 0.04 | h/m2 | 70.95 | m2 | 2.838 | h
|  | Placement of acoustical panels in theater walls |  | 1st official and ordinary pawn in construction |  | 0.04 | h/m2 | 540.45 | m2 | 21.618 | h
[6 empty] | TOTAL |  |  |  | 1393.3349 | H