Paleizenstraat 70

1030  Brussel

T 	+32 (0)2 250 11 82

T 	+32 (0)2 250 11 91

F 	+32 (0)2 250 11 11

E 	bouw.sintlukas@luca-arts.be

W 	http://www.luca-arts.be/bouw

June 2013	Martín-Palanco Gil, Eduardo

Bachelorproef Bouw

Planning

SUMMARY OF QUANTITIES

| WORK DESCRIPTION | Unit | X | Y | Z | N | Total |
| --- | --- | --- | --- | --- | --- | --- |
| COLUMNS Ø R+1 | m | 1 | 3,32 | 1 | 7 | 23,24 |
|  |  |  |  |  |  | 23,24 |
| CONCRETE WALLS R+1 | m² | 6,47 | 3,32 | 1 | 1 | 21,48 |
|  |  | 0,61 | 3,32 | 1 | 1 | 2,03 |
|  |  | 9,85 | 3,32 | 1 | 1 | 32,70 |
|  |  | 1,10 | 3,32 | 1 | 1 | 3,65 |
|  |  | 6,01 | 3,32 | 1 | 1 | 19,95 |
|  |  | 1,45 | 3,32 | 1 | 10 | 48,14 |
|  |  | 16,55 | 3,32 | 1 | 1 | 54,95 |
|  |  | 5,41 | 3,32 | 1 | 1 | 17,96 |
|  |  | 1,55 | 3,32 | 1 | 2 | 10,29 |
|  |  | 16,56 | 3,32 | 1 | 1 | 54,98 |
|  |  | 2,71 | 3,32 | 1 | 1 | 9,00 |
|  |  | 3,51 | 3,32 | 1 | 1 | 11,65 |
|  |  | 11,21 | 3,32 | 1 | 1 | 37,22 |
|  |  | 6,75 | 3,32 | 1 | 1 | 22,41 |
|  |  | -2,20 | 2,20 | 1 | 1 | -4,84 |
|  |  | 7,18 | 3,32 | 1 | 1 | 23,84 |
|  |  | -0,95 | 2,20 | 1 | 2 | -4,18 |
|  |  | 4,17 | 3,32 | 1 | 1 | 13,84 |
|  |  | 28,76 | 3,32 | 1 | 1 | 95,48 |
|  |  | 2,46 | 3,32 | 1 | 1 | 8,17 |
|  |  | 2,47 | 3,32 | 1 | 1 | 8,20 |
|  |  | 1,80 | 2,20 | 1 | 2 | 7,92 |
|  |  |  |  |  |  | 494,84 |
| BRICK WALLS/SILICATE R+1 | m² | 1,45 | 3,32 | 1 | 12 | 57,77 |
|  |  | 3,13 | 3,32 | 1 | 1 | 10,39 |
|  |  | 0,82 | 3,32 | 1 | 1 | 2,71 |
|  |  |  |  |  |  | 70,87 |
| BEAMS R+2 | m | 38,01 | 1 | 1 | 1 | 38,01 |
|  |  | 8,95 | 1 | 1 | 1 | 8,95 |
|  |  |  |  |  |  | 46,96 |
| PREFABRICATE CONCRETE SLABS+ FRESH CONCRETE R+2 | m² | 702,67 |  |  |  | 702,67 |
|  |  | -6,62 |  |  |  | -6,62 |
|  |  | -7,05 |  |  |  | -7,05 |
|  |  | -4,05 |  |  |  | -4,05 |
|  |  | -5,63 |  |  |  | -5,63 |
|  |  |  |  |  |  | 679,32 |
| THERMIC INSULATION | m² | 41,3 | 10,52 | 1 | 1 | 434,476 |
|  |  | 1 | 1 | -3,35 | 42 | -140,7 |
|  |  | 25,36 | 10,52 | 1 | 1 | 266,7872 |
|  |  | 1,8 | -2,72 | 1 | 9 | -44,064 |
|  |  | 1,33 | -2,72 | 1 | 3 | -10,8528 |
|  |  | 40,37 | 10,52 | 1 | 1 | 424,6924 |
|  |  | 1 | 1 | -3,35 | 39 | -130,65 |
|  |  | 14,3 | 10,52 | 1 | 1 | 150,436 |
|  |  | 2,71 | -1,24 | 1 | 3 | -10,0812 |
|  |  |  |  |  |  | 940,04 |
| BRICK FACADE | m² | 41,3 | 10,52 | 1 | 1 | 434,476 |
|  |  | 1 | 1 | -3,35 | 42 | -140,7 |
|  |  | 25,36 | 10,52 | 1 | 1 | 266,7872 |
|  |  | 1,8 | -2,72 | 1 | 9 | -44,064 |
|  |  | 1,33 | -2,72 | 1 | 3 | -10,8528 |
|  |  | 40,37 | 10,52 | 1 | 1 | 424,6924 |
|  |  | 1 | 1 | -3,35 | 39 | -130,65 |
|  |  | 14,3 | 10,52 | 1 | 1 | 150,436 |
|  |  | 2,71 | -1,24 | 1 | 3 | -10,0812 |
|  |  |  |  |  |  | 940,04 |
| TECHNICAL FLOOR+ ACOUSTIC INSULATION R+1 | m² | 126,88 |  |  |  | 126,88 |
|  |  | 449,04 |  |  |  | 449,04 |
|  |  | 20,36 |  |  |  | 20,36 |
|  |  | 37,05 |  |  |  | 37,05 |
|  |  |  |  |  |  | 633,33 |
| FALSE CEILING R+1 | m² | 126,88 |  |  |  | 126,88 |
|  |  | 449,04 |  |  |  | 449,04 |
|  |  | 20,36 |  |  |  | 20,36 |
|  |  | 37,05 |  |  |  | 37,05 |
|  |  |  |  |  |  | 633,33 |
| GREEN ROOF | m² | 289,69 |  |  |  | 289,69 |
|  |  |  |  |  |  | 289,69 |

PERFOMANCE – EFFICIENCY

| WORK DESCRIPTION | Performance / Efficiency | Unit | Measurement | Hours | Days | Real days |
| --- | --- | --- | --- | --- | --- | --- |
| COLUMNS Ø R+1 | 0,044 | h/m | 23,24 | 1,02 | 0,128 | 1 |
| CONCRETE WALLS R+1 | 0,65 | h/m² | 494,84 | 321,65 | 40,206 | 41 |
| BRICK WALLS/SILICATE R+1 | 0,6 | h/m² | 70,86 | 42,52 | 5,315 | 6 |
| BEAMS R+2 | 0,032 | h/m | 46,96 | 1,50 | 0,188 | 1 |
| PREFABRICATE CONCRETE SLABS+ FRESH CONCRETE R+2 | 0,161 | h/m² | 679,32 | 109,37 | 13,671 | 14 |
| THERMIC INSULATION | 0,05 | h/m² | 940,04 | 47,00 | 5,875 | 6 |
| BRICK FACADE | 0,072 | h/m² | 940,04 | 67,68 | 8,460 | 9 |
| TECHNICAL FLOOR+ ACOUSTIC INSULATION R+1 | 0,04 | h/m² | 633,33 | 25,33 | 3,167 | 4 |
| FALSE CEILING R+1 | 0,027 | h/m² | 633,33 | 17,10 | 2,137 | 3 |
| COLUMNS Ø R+2 | 0,044 | h/m | 23,24 | 1,02 | 0,128 | 1 |
| CONCRETE WALLS R+2 | 0,65 | h/m² | 494,84 | 321,65 | 40,206 | 41 |
| BRICK WALLS/SILICATE R+2 | 0,6 | h/m² | 70,86 | 42,52 | 5,315 | 6 |
| BEAMS R+3 | 0,032 | h/m | 46,96 | 1,50 | 0,188 | 1 |
| PREFABRICATE CONCRETE SLABS+ FRESH CONCRETE R+3 | 0,161 | h/m² | 679,32 | 109,37 | 13,671 | 14 |
| TECHNICAL FLOOR+ ACOUSTIC INSULATION R+2 | 0,04 | h/m² | 633,33 | 25,33 | 3,167 | 4 |
| FALSE CEILING R+2 | 0,027 | h/m² | 633,33 | 17,10 | 2,137 | 3 |
| COLUMNS Ø R+3 | 0,044 | h/m | 23,24 | 1,02 | 0,128 | 1 |
| CONCRETE WALLS R+3 | 0,65 | h/m² | 494,84 | 321,65 | 40,206 | 41 |
| BRICK WALLS/SILICATE R+3 | 0,6 | h/m² | 70,86 | 42,52 | 5,315 | 6 |
| BEAMS R+4 | 0,032 | h/m | 46,96 | 1,50 | 0,188 | 1 |
| PREFABRICATE CONCRETE SLABS+ FRESH CONCRETE R+4 | 0,161 | h/m² | 679,32 | 109,37 | 13,671 | 14 |
| TECHNICAL FLOOR+ ACOUSTIC INSULATION R+3 | 0,04 | h/m² | 633,33 | 25,33 | 3,167 | 4 |
| FALSE CEILING R+3 | 0,027 | h/m² | 633,33 | 17,10 | 2,137 | 3 |
| COLUMNS Ø R+4 | 0,044 | h/m | 23,24 | 1,02 | 0,128 | 1 |
| CONCRETE WALLS R+4 | 0,65 | h/m² | 494,84 | 321,65 | 40,206 | 41 |
| BRICK WALLS/SILICATE R+4 | 0,6 | h/m² | 70,86 | 42,52 | 5,315 | 6 |
| BEAMS ROOF | 0,032 | h/m | 46,96 | 1,50 | 0,188 | 1 |
| PREFABRICATE CONCRETE SLABS+ FRESH CONCRETE ROOF | 0,161 | h/m² | 679,32 | 109,37 | 13,671 | 14 |
| TECHNICAL FLOOR+ ACOUSTIC INSULATION R+4 | 0,04 | h/m² | 633,33 | 25,33 | 3,167 | 4 |
| FALSE CEILING R+4 | 0,027 | h/m² | 633,33 | 17,10 | 2,137 | 3 |
| GREEN ROOF | 0,44 | h/m² | 289,69 | 127,46 | 15,933 | 16 |

REFERENCES

Ive 2013 Catalogue. Instituto Valenciano de la Edificación.

- www.five.es

Columns

Concrete Walls

Bricks Walls / Silicate

Beams

Prefabricate concrete slabs + fresh concrete

Technical floor + acoustic insulation

False ceiling

Green roof

EXERCISE 2

DIFERENCIES BETWEEN EXTENSIVE AND INTENSIVE ROOF

Extensive – Also referred to as eco-roofs, and low-profile – They have thinner and less numbers of layers, so therefore they are lighter, less expensive and very low maintenance.  Extensive greenroofs are built when the primary desire is for an ecological roof cover with limited human access.  The minimum growing media or soil substrate starts at about 2 1/2” to 6” at most (although vegetative mats can actually have even less than 1" of growth media); the engineered soil media contains 70 – 80% inorganic or mineral material (or higher) to 20 – 30% organic (or less).  Low growing, horizontally spreading root ground covers with general maximum plant heights of 16 – 24” are ideal.  Alpine-type plants are successful because they are high drought, wind, frost, and heat tolerant, all necessary attributes for greenroofs.  Plants include sedums and other succulents, flowering herbs, and certain grasses and mosses.  Fully saturated weights range from a low of about 10 – 50 lbs/sq. ft.  Compare that to common river rock ballast which weighs about 12 lbs/sq. ft.  Extensive greenroofs can be constructed on slopes up to 30°, and steeper ones can be installed with raised grids or laths to hold plants and soil media in place.

Intensive – Also referred to as high-profile – They look like traditional roof gardens because a much wider variety of plant material can be included since growing media depths are increased.  The growing media starts from about 8 - 12” and can range up to 15 feet or more, depending on the loading capacity of the roof and the architectural and plant features that the building owner desires.  The engineered soil media usually contains about 45 - 50% organic material to 50 - 55% mineral, and fully saturated weights range from about 80 -120 lbs/sq. ft. and up.  Architectural accents such as waterfalls, ponds, gazebos, etc. are possible and these greenroofs provide recreation spaces and encourage interaction between people and nature.  Maintenance requirements are also more intensive, and of course, these roofs are relatively flat.

INTENSIVE GREEN ROOF DESCRIPTION

Flat roof garden made ​​of cellular concrete layer for forming slopes between 1 and 5%, regularization layer thickness 2cm waterproofing cement mortar, bituminous emulsion black primer ED type and performance of not less than 0.3 kg/m2, adhered waterproofing with torch, type A2, type foil LBM-40-FP type elastomeric SBS modified bitumen, thermal insulation panel composed of rigid extruded polystyrene (XPS) of 50mm thick and K = 0.027 W / mK, anti-sharp layer with geotextile polyester felt, laying 20cm thick gravel, geotextile filter layer and routing with 20cm of topsoil for planting, including pre-cleaning of the support, staking, training bibs, sinks in filter boxes made ​​of brick 50x50cm drilled and manhole cover frame and metal mesh painted, wastage and overlaps, according to UNE-104.

| QUANTITY | UNIT | DESCRIPTION | PRICE | AMOUNT |
| --- | --- | --- | --- | --- |
| 0.440 | h | 1st official construction | R | 10.08 |
| 1.640 | h | Pawn specialized construction | 22.29 | 36.56 |
| 0.500 | kg | Black bituminous emulsion type ED | 1.26 | 0.63 |
| 1.150 | m2 | LBM (SBS)-40-FP PE | 9.80 | 11.27 |
| 2.100 | m2 | Geotextile FP-120gr/m2 | 0.60 | 1.26 |
| 0.400 | m | Anti-sharp 50 bitumen layer | 7.52 | 3.01 |
| 0.070 | m | Precast cord 20mm BH-II | 2.07 | 0.14 |
| 0.070 | m | Anti-sharp 33 bitumen layer | 3.11 | 0.22 |
| 0.120 | m3 | Cellular concrete | 51.33 | 6.16 |
| 0.340 | t | Limestone gravel 10/25 s/lvd 10km | 12,29 | 4.18 |
| 0.200 | m3 | Topsoil for planting | 6.54 | 1.31 |
| 6.500 | u | Hollow brick 24x11.5x9 | 0.18 | 1.17 |
| 3.800 | u | Hollow brick 24x11.5x4 | 0.13 | 0.49 |
| 4.000 | u | Perforated brick 24x11.5x9 | 0.17 | 0.68 |
| 0.040 | u | Drain Ø 80mm | 23.93 | 0.96 |
| 0.010 | m2 | Reticular mesh 40x40mm | 37.70 | 0.38 |
| 0.040 | m3 | Waterproofing cement mortar | 125.54 | 5.02 |
| 0.020 |  | Addicional direct costs | 83.56 | 1.67 |
| 1.050 | m2 | Mineral wool | 20.45 | 21.47 |
|  |  |  |  | 106.66 |

TOTAL PRICE INCLUDING LABOR AND TAXES

106.66(euros) x 290.11(m2) = 30943.13 Euros

NO PASSABLE ROOF

Roof Autoprotected not passable for training on foil vapor barrier attached flame on primer, 14cm layer cellular concrete slope formation between 1 <p <= 5%, adjustment layer with thickness 2cm waterproof mortar , black bitumen emulsion primer type ED and not less than 0.3kg/m2 performance, monolayer solution adhering waterproofing with torch, foil type modified bitumen LBM-50/G-FP 50gr/dm2 total mass, self-protected with granules colored minerals and armed with polyester felt, even after cleaning the substrate, staking, training bibs, sinks and other specials with foil strips LBM-40-FP, adhered with torch placed prior primer, wastage, overlaps, as HS DB -1 CTE and UNE-104.

| QUANTITY | UNIT | DESCRIPTION | PRICE | AMOUNT |
| --- | --- | --- | --- | --- |
| 0.510 | h | 1st official construction | 22.91 | 11.68 |
| 0.510 | h | Pawn specialized construction | 22.29 | 11.37 |
| 1.000 | kg | Black bituminous emulsion type ED | 1.26 | 1.26 |
| 1.200 | m2 | LBM (SBS)-40-FP PE | 12.72 | 15.26 |
| 1.100 | m | Anti-sharp 50 bitumen layer | 6.66 | 7.33 |
| 0.300 | m | Precast cord 20mm BH-II | 2.07 | 0.62 |
| 0.300 | m | Anti-sharp 33 bitumen layer | 3.11 | 0.93 |
| 0.400 | m | Anti-sharp 50 bitumen layer | 7.52 | 3.01 |
| 0.147 | m3 | Cellular concrete | 51.33 | 7.55 |
| 0.040 | u | Drain Ø 80mm | 19.90 | 0.64 |
| 8.000 | u | Hollow brick 24x11.5x9 | 0.18 | 1.44 |
| 3.800 | u | Hollow brick 24x11.5x4 | 0.13 | 0.49 |
| 0.030 | m3 | Waterproofing cement mortar | 125.54 | 3.77 |
| 0.020 |  | Addicional direct costs | 65.35 | 1.31 |
|  |  |  |  | 66.66 |

TOTAL PRICE INCLUDING LABOR AND TAXES

66.66(euros) x 290.11(m2) = 19338.73 Euros

DIFFERENCE BETWEEN ROOFS

30943.13 - 19338.73 = 11604.40 Euros