## Sheet1
Calculation of arch.fee:
Construction costs | 7468196.25
Fee %: | 10%
Fee in DKK: | 746819.625 | ≈ | 210%
Margin in %: | 110% |  | 391191.2321
Variable costs.: | 100% |  | 355628.3929
Insert actual variable costs for the following phases:
Outline phase | 18773.0061
Scheme design phase | 38429.4479
Detail Design 1 | 35337.4233
Detail Design 2
Follow-up (client´s site inspection)
Week no.: | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
Phase: | Outline phase 20% |  |  |  | Scheme Design 25% | [8 empty] | DD1 25% |  |  |  | Follow-up 15%
Distribution of fee/wk. | 37340.9813 | 37340.9813 | 37340.9813 | 37340.9813 | 26672.1295 | 26672.1295 | 26672.1295 | 26672.1295 | 26672.1295 | 26672.1295 | 26672.1295 | 56011.4719 | 56011.4719 | 46676.2266 | 46676.2266 | 46676.2266 | 46676.2266 | 37340.9812 | 37340.9812 | 37340.9812
Cumulative fee: | 37340.9813 | 74681.9625 | 112022.9438 | 149363.925 | 176036.0545 | 202708.1839 | 229380.3134 | 256052.4429 | 282724.5723 | 309396.7018 | 336068.8313 | 392080.3031 | 448091.775 | 494768.0016 | 541444.2281 | 588120.4547 | 634796.6813 | 672137.6625 | 709478.6437 | 746819.625
variable costs/week (wages for design team): | 17781.4196 | 17781.4196 | 17781.4196 | 17781.4196 | 12701.014 | 12701.014 | 12701.014 | 12701.014 | 12701.014 | 12701.014 | 12701.014 | 26672.1295 | 26672.1295 | 22226.7746 | 22226.7746 | 22226.7746 | 22226.7746 | 17781.4196 | 17781.4196 | 17781.4196
Cumulative variable costs: | 17781.4196 | 35562.8393 | 53344.2589 | 71125.6786 | 83826.6926 | 96527.7066 | 109228.7207 | 121929.7347 | 134630.7487 | 147331.7628 | 160032.7768 | 186704.9062 | 213377.0357 | 235603.8103 | 257830.5848 | 280057.3594 | 302284.1339 | 320065.5536 | 337846.9732 | 355628.3929
Cumulative margin: | 19559.5616 | 39119.1232 | 58678.6848 | 78238.2464 | 92209.3619 | 106180.4773 | 120151.5927 | 134122.7082 | 148093.8236 | 162064.939 | 176036.0545 | 205375.3969 | 234714.7393 | 259164.1913 | 283613.6433 | 308063.0953 | 332512.5473 | 352072.1089 | 371631.6705 | 391191.2321
Aktuelt V.O: | 9607.362 | 9607.362 | 9607.362 | 9607.362 | 5489.9211 | 5489.9211 | 5489.9211 | 5489.9211 | 5489.9211 | 5489.9211 | 5489.9211 | 17668.7117 | 17668.7117 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative actual V.C.: | 9607.362 | 19214.7239 | 28822.0859 | 38429.4479 | 43919.369 | 49409.2901 | 54899.2112 | 60389.1323 | 65879.0535 | 71368.9746 | 76858.8957 | 94527.6074 | 112196.319 | 112196.319 | 112196.319 | 112196.319 | 112196.319 | 112196.319 | 112196.319 | 112196.319
Note on B9: eml: Link til MSP
Note on B10: eml: Link til MSP
Note on B11: eml: Link til MSP
Note on B12: eml: Link til MSP

## Pp outline
Personal planning of outline proposal
Wage/Hr | 220.8589
Activity/Wr nr |  | 6 | 7 | 8 | 9 | 10 | Total hr | Actual costs/hr
Sketching | Planned
| Actual | [5 empty] | 0 | 0
Details | Planned
| Actual | [5 empty] | 0 | 0
[8 empty] | 0 | Sheet 1, fase d'outline.

## Pp scheme design
Personal planning of outline proposal
Wage/Hr | 220.8589
Activity/Wr nr |  | M-T-W-T-F | 11 | M-T-W-T-F | 12 | M-T-W-T-F | 13 | M-T-W-T-F | 14 | M-T-W-T-F | 15 | 16 | 17 | 18 | 19 | 20 | 21 | Total hr | Actual costs/hr
Sketching | Planned | 2-2-2-2-2 |  | 4-4-2-4-4 |  | 4-4-2-4-4 |  | 4-4-2-4-4 |  | 4-4-2-4-4 | 16: 4-4-2-4-4
| Actual | 0-2-0-3-2 | [15 empty] | #VALUE! | #VALUE!
Details | Planned | 2-2-2-2-2
| Actual | 0-1-0-0-1 | [15 empty] | #VALUE! | #VALUE!
Sections | Planned | 0-0-0-0-0
| Actual | 0-0-0-0-0
3D Models | Planned | 0-0-0-0-0
| Actual | 0-0-0-0-0
[19 empty] | #VALUE! | Sheet 1, fase d'scheme design

## Hoja1
SCHEME DESIGN PLANNING
|  | OUTLINE | [26 empty] | SCHEME DESIGN | [62 empty] | FINAL
|  | 7 |  |  |  |  | WEEK | 8 |  |  |  |  | WEEK | 9 |  |  |  |  | WEEK | 10 |  |  |  |  | WEEK | total hours |  | total kr | 11 |  |  |  |  | WEEK | 12 |  |  |  |  | WEEK | 13 |  |  |  |  | WEEK | 14 |  |  |  |  | WEEK | 15 |  |  |  |  | WEEK | 16 |  |  |  |  | WEEK | 17 |  |  |  |  | WEEK | 18 |  |  |  |  | WEEK | 19 |  |  |  |  | WEEK | 20 |  |  |  |  | WEEK | total hours |  | total kr | 21 |  |  |  |  | WEEK | 22 |  |  |  |  | WEEK | 23 |  |  |  |  | WEEK | 24 |  |  |  |  | WEEK | total hours |  | total kr
|  | MON | TUE | WED | THU | FRI |  | MON | TUE | WED | THU | FRI |  | MON | TUE | WED | THU | FRI |  | MON | TUE | WED | THU | FRI |  |  |  |  | MON | TUE | WED | THU | FRI |  | MON | TUE | WED | THU | FRI |  | MON | TUE | WED | THU | FRI |  | MON | TUE | WED | THU | FRI |  | MON | TUE | WED | THU | FRI |  | MON | TUE | WED | THU | FRI |  | MON | TUE | WED | THU | FRI |  | MON | TUE | WED | THU | FRI |  | MON | TUE | WED | THU | FRI |  | MON | TUE | WED | THU | FRI |  |  |  |  | MON | TUE | WED | THU | FRI |  | MON | TUE | WED | THU | FRI |  | MON | TUE | WED | THU | FRI |  | MON | TUE | WED | THU | FRI
SKETCHING | PLANNED | 2 | 2 | 2 | 2 | 2 | 10 | 2 | 2 | 2 | 2 | 2 | 10 | 2 | 2 | 0 | 2 | 2 | 8 | 3 | 1 | 1 | 3 | 2 | 10 | 38 | 220.8589 | 8392.638 | 2 | 2 | 2 | 2 | 2 | 10 | 2 | 2 | 2 | 2 | 2 | 10 | 2 | 2 | 0 | 2 | 2 | 8 | 3 | 1 | 1 | 3 | 2 | 10 | 3 | 3 | 3 | 3 | 3 | 15 | 2 | 2 | 2 | 2 | 2 | 10 | 1 | 3 | 2 | 2 | 0 | 8 | 1 | 3 | 0 | 0 | 4 | 8 | 1 | 3 | 2 | 2 | 0 | 8 | 2 | 2 | 2 | 2 | 2 | 10 | 59 | 220.8589 | 13030.6748 | 3 | 3 | 2 | 2 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 220.8589 | 2208.589
| ACTUAL | 0 | 2 | 0 | 3 | 3 | 8 | 1 | 2 | 1 | 2 | 1 | 7 | 2 | 2 | 0 | 1 | 2 | 7 | 2 | 2 | 1 | 1 | 2 | 8 | 30 | 220.8589 | 6625.7669 | 3 | 3 | 2 | 3 | 3 | 14 | 1 | 2 | 1 | 2 | 1 | 7 | 2 | 2 | 0 | 1 | 2 | 7 | 2 | 2 | 1 | 1 | 2 | 8 | 3 | 3 | 3 | 3 | 3 | 15 | 1 | 1 | 1 | 2 | 2 | 7 | 1 | 3 | 2 | 2 | 0 | 8 | 1 | 3 | 3 | 3 | 0 | 10 | 1 | 3 | 1 | 3 | 3 | 11 | 2 | 3 | 2 | 3 | 2 | 12 | 63 | 220.8589 | 13914.1104 | 1 | 3 | 2 | 2 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 220.8589 | 1766.8712
DETAILS | PLANNED | 2 | 2 | 2 | 2 | 2 | 10 | 2 | 2 | 2 | 2 | 2 | 10 | 2 | 2 | 0 | 2 | 2 | 8 | 2 | 1 | 1 | 2 | 1 | 7 | 35 | 220.8589 | 7730.0613 | 2 | 2 | 2 | 2 | 2 | 10 | 2 | 2 | 2 | 2 | 2 | 10 | 2 | 2 | 0 | 2 | 2 | 8 | 2 | 1 | 1 | 2 | 1 | 7 | 1 | 1 | 1 | 1 | 1 | 5 | 2 | 2 | 2 | 2 | 0 | 8 | 1 | 3 | 2 | 1 | 2 | 9 | 1 | 3 | 4 | 4 | 4 | 16 | 2 | 3 | 2 | 2 | 2 | 11 | 2 | 2 | 2 | 2 | 2 | 10 | 59 | 220.8589 | 13030.6748 | 1 | 3 | 2 | 1 | 2 | 9 | 1 | 3 | 0 | 3 | 0 | 7 | 2 | 3 | 2 | 2 | 2 | 11 | 2 | 2 | 2 | 2 | 2 | 10 | 37 | 220.8589 | 8171.7791
| ACTUAL | 0 | 0 | 0 | 2 | 2 | 4 | 2 | 2 | 0 | 2 | 2 | 8 | 2 | 2 | 0 | 2 | 2 | 8 | 0 | 2 | 2 | 2 | 0 | 6 | 26 | 220.8589 | 5742.3313 | 3 | 3 | 3 | 3 | 2 | 14 | 2 | 2 | 1 | 2 | 2 | 9 | 2 | 2 | 0 | 2 | 2 | 8 | 0 | 2 | 2 | 2 | 0 | 6 | 1 | 1 | 1 | 1 | 1 | 5 | 2 | 2 | 2 | 2 | 0 | 8 | 1 | 3 | 2 | 1 | 2 | 9 | 1 | 3 | 2 | 2 | 2 | 10 | 1 | 3 | 3 | 2 | 2 | 11 | 2 | 3 | 2 | 3 | 3 | 13 | 56 | 220.8589 | 12368.0982 | 1 | 3 | 2 | 1 | 2 | 9 | 1 | 3 | 4 | 4 | 2 | 14 | 4 | 3 | 3 | 4 | 4 | 18 | 4 | 3 | 2 | 4 | 3 | 16 | 57 | 220.8589 | 12588.9571
BPM | PLANNED | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 5 | 2 | 2 | 1 | 2 | 2 | 9 | 2 | 2 | 2 | 2 | 2 | 10 | 24 | 220.8589 | 5300.6135 | 1 | 2 | 1 | 1 | 2 | 7 | 1 | 1 | 1 | 1 | 1 | 5 | 2 | 2 | 1 | 2 | 2 | 9 | 2 | 2 | 2 | 2 | 2 | 10 | 0 | 0 | 2 | 2 | 2 | 6 | 1 | 1 | 0 | 1 | 1 | 4 | 4 | 0 | 2 | 0 | 0 | 6 | 4 | 0 | 2 | 0 | 0 | 6 | 4 | 2 | 2 | 2 | 2 | 12 | 2 | 2 | 2 | 2 | 2 | 10 | 44 | 220.8589 | 9717.7914 | 4 | 0 | 2 | 0 | 0 | 6 | 4 | 0 | 2 | 2 | 2 | 10 | 4 | 2 | 2 | 2 | 2 | 12 | 2 | 2 | 2 | 2 | 2 | 10 | 38 | 220.8589 | 8392.638
| ACTUAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 1 | 1 | 6 | 1 | 2 | 1 | 1 | 2 | 7 | 13 | 220.8589 | 2871.1656 | 3 | 3 | 3 | 3 | 3 | 15 | 2 | 3 | 2 | 3 | 2 | 12 | 2 | 1 | 1 | 1 | 1 | 6 | 1 | 2 | 1 | 1 | 2 | 7 | 3 | 0 | 1 | 2 | 2 | 8 | 1 | 1 | 0 | 1 | 1 | 4 | 4 | 3 | 3 | 0 | 0 | 10 | 4 | 3 | 2 | 2 | 0 | 11 | 4 | 1 | 1 | 3 | 2 | 11 | 4 | 3 | 2 | 2 | 0 | 11 | 55 | 220.8589 | 12147.2393 | 4 | 3 | 3 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 0 | 4 | 4 | 3 | 3 | 3 | 2 | 15 | 4 | 3 | 2 | 2 | 3 | 14 | 43 | 220.8589 | 9496.9325
INSTALLATIONS | PLANNED | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 4 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 220.8589 | 1325.1534 | 1 | 2 | 1 | 2 | 1 | 7 | 1 | 1 | 1 | 0 | 1 | 4 | 1 | 0 | 1 | 0 | 0 | 2 | 1 | 3 | 2 | 0 | 2 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 10 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 2 | 2 | 2 | 8 | 2 | 2 | 2 | 2 | 2 | 10 | 32 | 220.8589 | 7067.4847 | 2 | 2 | 2 | 2 | 2 | 10 | 2 | 2 | 2 | 2 | 2 | 10 | 3 | 3 | 3 | 3 | 3 | 15 | 3 | 3 | 3 | 2 | 2 | 13 | 48 | 220.8589 | 10601.227
| ACTUAL | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 0 | 2 | 6 | 1 | 0 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 8 | 16 | 220.8589 | 3533.7423 | 3 | 3 | 3 | 2 | 2 | 13 | 1 | 2 | 1 | 0 | 2 | 6 | 1 | 3 | 1 | 2 | 2 | 9 | 2 | 2 | 2 | 2 | 3 | 11 | 0 | 3 | 0 | 3 | 3 | 9 | 0 | 0 | 2 | 2 | 2 | 6 | 0 | 0 | 0 | 2 | 0 | 2 | 3 | 3 | 2 | 3 | 3 | 14 | 0 | 3 | 2 | 0 | 3 | 8 | 2 | 2 | 3 | 1 | 3 | 11 | 50 | 220.8589 | 11042.9448 | 3 | 3 | 3 | 3 | 3 | 15 | 2 | 2 | 3 | 2 | 2 | 11 | 2 | 3 | 2 | 3 | 3 | 13 | 3 | 3 | 2 | 2 | 3 | 13 | 52 | 220.8589 | 11484.6626
TOTAL | PLANNED | 4 | 4 | 4 | 4 | 4 | 20 | 6 | 6 | 6 | 5 | 6 | 29 | 7 | 6 | 2 | 6 | 6 | 27 | 7 | 4 | 4 | 7 | 5 | 27 | 103 | 220.8589 | 22748.4663 | 6 | 8 | 6 | 7 | 7 | 34 | 6 | 6 | 6 | 5 | 6 | 29 | 7 | 6 | 2 | 6 | 6 | 27 | 8 | 7 | 6 | 7 | 7 | 35 | 4 | 4 | 6 | 6 | 6 | 26 | 7 | 7 | 6 | 7 | 5 | 32 | 6 | 6 | 6 | 5 | 2 | 25 | 6 | 6 | 8 | 4 | 8 | 32 | 7 | 10 | 8 | 8 | 6 | 39 | 8 | 8 | 8 | 8 | 8 | 40 | 194 | 220.8589 | 42846.6258 | 10 | 8 | 8 | 5 | 4 | 35 | 7 | 5 | 4 | 7 | 4 | 27 | 9 | 8 | 7 | 7 | 7 | 38 | 7 | 7 | 7 | 6 | 6 | 33 | 133 | 220.8589 | 29374.2331
| ACTUAL | 0 | 2 | 0 | 5 | 5 | 12 | 4 | 6 | 14 | 4 | 5 | 21 | 7 | 5 | 2 | 4 | 5 | 23 | 5 | 8 | 6 | 6 | 4 | 29 | 85 | 220.8589 | 18773.0061 | 12 | 12 | 11 | 11 | 10 | 56 | 6 | 9 | 17 | 7 | 7 | 34 | 7 | 8 | 2 | 6 | 7 | 30 | 5 | 8 | 6 | 6 | 7 | 32 | 7 | 7 | 5 | 9 | 9 | 37 | 4 | 4 | 5 | 7 | 5 | 25 | 6 | 9 | 7 | 5 | 2 | 29 | 9 | 12 | 9 | 10 | 5 | 45 | 6 | 10 | 7 | 8 | 10 | 41 | 10 | 11 | 9 | 9 | 8 | 47 | 224 | 220.8589 | 49472.3926 | 9 | 12 | 10 | 6 | 5 | 42 | 7 | 5 | 7 | 6 | 4 | 29 | 10 | 9 | 8 | 10 | 9 | 46 | 11 | 9 | 6 | 8 | 9 | 43 | 160 | 220.8589 | 35337.4233
|  |  |  | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
[48 empty] | 0 | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40
[45 empty] | week number |  |  | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
[45 empty] | planned |  |  | 20 | 29 | 27 | 27 | 34 | 29 | 27 | 35 | 26 | 32 | 25 | 36 | 39 | 40 | 35 | 27 | 38 | 33
[45 empty] | actual |  |  | 12 | 21 | 23 | 29 | 36 | 34 | 30 | 32 | 37 | 25 | 29 | 45 | 41 | 47 | 42 | 29 | 46 | 43