## Sheet1
Calculation of arch.fee:
Construction costs | 5000000
Fee %: | 10%
Fee in DKK: | 500000 | ≈ | 210%
Margin in %: | 110% |  | 261904.7619
Variable costs.: | 100% |  | 238095.2381
Insert actual variable costs for the following phases:
Outline phase | 20000
Scheme design phase | 70000
Detail Design 1
Detail Design 2
Follow-up (client´s site inspection)
Week no.: | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
Phase: | Outline phase 20% |  |  |  | Scheme Design 25% | [6 empty] | DD1 15% |  | DD2 25% |  |  |  | Follow-up 15%
Distribution of fee/wk. | 25000 | 25000 | 25000 | 25000 | 17857.1429 | 17857.1429 | 17857.1429 | 17857.1429 | 17857.1429 | 17857.1429 | 17857.1429 | 37500 | 37500 | 31250 | 31250 | 31250 | 31250 | 25000 | 25000 | 25000
Cumulative fee: | 25000 | 50000 | 75000 | 100000 | 117857.1429 | 135714.2857 | 153571.4286 | 171428.5714 | 189285.7143 | 207142.8571 | 225000 | 262500 | 300000 | 331250 | 362500 | 393750 | 425000 | 450000 | 475000 | 500000
variable costs/week (wages for design team): | 11904.7619 | 11904.7619 | 11904.7619 | 11904.7619 | 8503.4014 | 8503.4014 | 8503.4014 | 8503.4014 | 8503.4014 | 8503.4014 | 8503.4014 | 17857.1429 | 17857.1429 | 14880.9524 | 14880.9524 | 14880.9524 | 14880.9524 | 11904.7619 | 11904.7619 | 11904.7619
Cumulative variable costs: | 11904.7619 | 23809.5238 | 35714.2857 | 47619.0476 | 56122.449 | 64625.8503 | 73129.2517 | 81632.6531 | 90136.0544 | 98639.4558 | 107142.8571 | 125000 | 142857.1429 | 157738.0952 | 172619.0476 | 187500 | 202380.9524 | 214285.7143 | 226190.4762 | 238095.2381
Cumulative margin: | 13095.2381 | 26190.4762 | 39285.7143 | 52380.9524 | 61734.6939 | 71088.4354 | 80442.1769 | 89795.9184 | 99149.6599 | 108503.4014 | 117857.1429 | 137500 | 157142.8571 | 173511.9048 | 189880.9524 | 206250 | 222619.0476 | 235714.2857 | 248809.5238 | 261904.7619
Aktuelt V.O: | 5000 | 5000 | 5000 | 5000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative actual V.C.: | 5000 | 10000 | 15000 | 20000 | 30000 | 40000 | 50000 | 60000 | 70000 | 80000 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000
Note on B8: eml: Link til MSP
Note on B9: eml: Link til MSP
Note on B10: eml: Link til MSP
Note on B11: eml: Link til MSP
Note on B12: eml: Link til MSP

## Pp outline
Personal planning of outline proposal
Wage/Hr | 220.8589
Activity/Wr nr |  | 6 | 7 | 8 | 9 | 10 | Total hr | Actual costs/hr
Sketching | Planned
| Actual | [5 empty] | 0 | 0
Details | Planned
| Actual | [5 empty] | 0 | 0
[8 empty] | 0 | Sheet 1, fase d'outline.

## Pp scheme design
Personal planning of outline proposal
Wage/Hr | 220.8589
Activity/Wr nr |  | M-T-W-T-F | 11 | M-T-W-T-F | 12 | M-T-W-T-F | 13 | M-T-W-T-F | 14 | M-T-W-T-F | 15 | 16 | 17 | 18 | 19 | 20 | 21 | Total hr | Actual costs/hr
Sketching | Planned | 2-2-2-2-2 |  | 4-4-2-4-4 |  | 4-4-2-4-4 |  | 4-4-2-4-4 |  | 4-4-2-4-4 | 16: 4-4-2-4-4
| Actual | 0-2-0-3-2 | [15 empty] | #VALUE! | #VALUE!
Details | Planned | 2-2-2-2-2
| Actual | 0-1-0-0-1 | [15 empty] | #VALUE! | #VALUE!
Sections | Planned | 0-0-0-0-0
| Actual | 0-0-0-0-0
3D Models | Planned | 0-0-0-0-0
| Actual | 0-0-0-0-0
[19 empty] | #VALUE! | Sheet 1, fase d'scheme design

## Hoja1
SCHEME DESIGN PLANNING
|  |  | 11 |  |  |  |  | WEEK | 12 |  |  |  |  | WEEK | 13 |  |  |  |  | WEEK | 14 |  |  |  |  | WEEK | 15 |  |  |  |  | WEEK | 16 |  |  |  |  | WEEK | 17 |  |  |  |  | WEEK | 18 |  |  |  |  | WEEK | 19 |  |  |  |  | WEEK | 20 |  |  |  |  | WEEK
|  |  | MON | TUE | WED | THU | FRI |  | MON | TUE | WED | THU | FRI |  | MON | TUE | WED | THU | FRI |  | MON | TUE | WED | THU | FRI |  | MON | TUE | WED | THU | FRI |  | MON | TUE | WED | THU | FRI |  | MON | TUE | WED | THU | FRI |  | MON | TUE | WED | THU | FRI |  | MON | TUE | WED | THU | FRI |  | MON | TUE | WED | THU | FRI
| SKETCHING | PLANNED | 2 | 2 | 2 | 2 | 2 | 10 | 2 | 2 | 2 | 2 | 2 | 10 | 2 | 2 | 0 | 2 | 2 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 15 | 2 | 2 | 2 | 2 | 2 | 10 | 1 | 3 | 2 | 2 | 0 | 8 | 1 | 3 | 0 | 0 | 0 | 4 | 1 | 3 | 2 | 2 | 0 | 8 | 2 | 2 | 2 | 2 | 2 | 10
|  | ACTUAL | 0 | 2 | 0 | 3 | 3 | 8 | 1 | 2 | 1 | 2 | 1 | 7 | 2 | 2 | 0 | 1 | 2 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 15 | 1 | 1 | 1 | 2 | 2 | 7 | 1 | 3 | 2 | 2 | 0 | 8 | 1 | 3 | 0 | 0 | 0 | 4 | 1 | 3 | 1 | 3 | 0 | 8 | 2 | 3 | 2 | 3 | 2 | 12
| DETAILS | PLANNED | 2 | 2 | 2 | 2 | 2 | 10 | 2 | 2 | 2 | 2 | 2 | 10 | 2 | 2 | 0 | 2 | 2 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 5 | 2 | 2 | 2 | 2 | 0 | 8 | 1 | 3 | 2 | 1 | 2 | 9 | 1 | 3 | 0 | 0 | 0 | 4 | 2 | 3 | 2 | 2 | 2 | 11 | 2 | 2 | 2 | 2 | 2 | 10
|  | ACTUAL | 0 | 0 | 0 | 2 | 2 | 4 | 2 | 2 | 0 | 2 | 2 | 8 | 2 | 2 | 0 | 2 | 2 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 5 | 2 | 2 | 2 | 2 | 0 | 8 | 1 | 3 | 2 | 1 | 2 | 9 | 1 | 3 | 0 | 0 | 2 | 6 | 1 | 3 | 3 | 2 | 2 | 11 | 2 | 3 | 2 | 3 | 3 | 13
| BPM | PLANNED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 2 | 2 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 6 | 1 | 1 | 0 | 1 | 1 | 4 | 4 | 0 | 2 | 0 | 0 | 6 | 4 | 0 | 2 | 0 | 0 | 6 | 4 | 2 | 2 | 2 | 2 | 12 | 2 | 2 | 2 | 2 | 2 | 10
|  | ACTUAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 1 | 1 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 5 | 1 | 1 | 0 | 1 | 1 | 4 | 4 | 3 | 3 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 0 | 4 | 4 | 1 | 1 | 3 | 2 | 11 | 4 | 0 | 2 | 2 | 0 | 8
| INSTALLATIONS | PLANNED | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 4 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 10 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 2 | 2 | 2 | 8 | 2 | 2 | 2 | 2 | 2 | 10
|  | ACTUAL | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 0 | 2 | 6 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 6 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 3 | 5 | 2 | 2 | 3 | 1 | 3 | 11
| TOTAL | PLANNED | 4 | 4 | 4 | 4 | 4 | 20 | 5 | 5 | 5 | 4 | 5 | 24 | 7 | 6 | 2 | 6 | 6 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 6 | 6 | 6 | 26 | 7 | 7 | 6 | 7 | 5 | 32 | 6 | 6 | 6 | 5 | 2 | 25 | 6 | 6 | 4 | 0 | 0 | 16 | 7 | 10 | 8 | 8 | 6 | 39 | 8 | 8 | 8 | 8 | 8 | 40
|  | ACTUAL | 0 | 2 | 0 | 5 | 5 | 12 | 4 | 6 | 12 | 4 | 5 | 21 | 7 | 5 | 2 | 4 | 5 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 5 | 6 | 6 | 25 | 4 | 4 | 5 | 7 | 5 | 25 | 6 | 9 | 7 | 5 | 2 | 29 | 6 | 6 | 2 | 0 | 2 | 16 | 6 | 7 | 7 | 8 | 7 | 35 | 10 | 8 | 9 | 9 | 8 | 44
|  |  |  | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
[26 empty] | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
[26 empty] | 20 | 24 | 27 | 0 | 26 | 32 | 25 | 16 | 39 | 40
[26 empty] | 12 | 21 | 23 | 0 | 25 | 25 | 29 | 16 | 35 | 44