1. Architectural Part	Page 1

1.1 Descriptive Memory	Page 2

1.1.1 Introduction	Page 2

1.1.2 Location	Page 2

1.1.3 Field	Page 4

1.1.4 Distribution Of The Floors	Page 4

1.2 Constructive Memory	Page 5

1.2.1 Foundation	Page 5

1.2.2 Columns	Page 7

1.2.3 Walls	Page 8

1.2.4 Roof	Page 8

1.2.5 Slabs	Page 8

1.2.6 Internal Walls And Partitions	Page 11

1.2.7 Stairs	Page 11

1.2.8 Façade	Page 12

1.2.9 Instalations	Page 12

1.2.10 Fire Safety	Page 13

1.2.11 Health Conditions	Page 13

1.2.12 Environment	Page 13

1.2.13 Disability Needs	Page 13

2. Technological Cards	Page 14

2.1 Technological Card Of Foundation	Page 15

2.1.1 General Description	Page 16

2.1.2 Description Of Tecnology

And Sequence Of Works	Page 16

2.1.3 Human Safety	Page 19

2.1.4 Material-Technical Resources	Page 20

2.1.5 Quality Control	Page 20

2.1.6 Labor Safety	Page 22

2.1.7 Budget	Page 26

2.1.7 Organization	Page 28

2.2 Technological Card Of Assembling Of Frame	Page 29

2.2.1 General Description	Page 30

2.2.2 Description Of Tecnology And

Sequence Of Works	Page 30

2.2.3 Human Safety	Page 33

2.2.4 Material-Technical Resources	Page 33

2.2.5 Quality Control	Page 34

2.2.6 Labor Safety	Page 35

2.2.7 Budget	Page 37

2.2.7 Organization	Page 40

2.3 Technological Card Of Curtain Wall	Page 41

2.3.1 General Description	Page 42

2.3.2 Description Of Tecnology And

Sequence Of Works	Page 42

2.3.3 Human Safety	Page 44

2.3.4 Material-Technical Resources	Page 44

2.3.5 Quality Control	Page 45

2.3.6 Labor Safety	Page 49

2.3.7 Budget	Page 52

2.3.7 Organization	Page 53

3.Organization Part	Page 55

3.1 Description Of The Territory	Page 56

3.2 Selection Of Tower Crane	Page 57

3.3 Setting Of Dangerous Zone	Page 63

3.4 Temporary Roads To The Building Place	Page 66

3.5 Temporary Storage Buildings And Sites	Page 66

3.6 Temporary Buildings For Workers And Managing	Page 66

3.7 Temporary Electricity Supply	Page 67

3.8 Consruction Site Lightning	Page 67

3.9 Temporary Water Supply	Page 68

3.10 Temporary Sewerage	Page 69

3.11 Fence Of Construction Field	Page 69

3.12 Temporary Comunications	Page 69

3.13 General Requirements Of Labor Safety	Page 70

3.14 Environmental Protection Requiremnts	Page 71

3.15 Fire Protection Requirements	Page 71

3.Bibliography	Page 72