COMPANY

Company’s safety handbook: contains and organization chart indicating who is responsible for what at the building site, a time schedule for safety meetings.

TENDERING

- Scrutiny of tender documents

- Define which parts of the Project will be carried out as “own production” and which parts will be carried out by subcontractors

- The contractor analyses the documents in order to identify any conditions that may not be expedient to the main contractor. The contractor can make reservations in the tender, ask questions or not take part in the tender at all.

- General Conditions AB92

- The contractor should call attention to errors or shortcomings he might find in the tender documents.

- The tender takes place in accordance with the Danish Act on Tender Procedures.

- Client Private or public?

- Is the contract sum above the threshold value?

- Type of tender.

- Define awarding criteria.

Tender subcontractors:

- Tender governed by Danish Contract Act

- Invitation to tender for the subcontractors

- Private clients are not affected by the Danish Act of Tender Procedures but may choose to comply with the act.

If they don’t comply with the act, the they comply to the Danish Contracts Act.

- Public client (state, Municipality): the main contractor must use the Danish Act on Tender

Timeline:

It is a planning tool which helps to ensure the project phases are implemented according to the time schedule.

It is elaborated on the basis of the tender time schedule, which provides information about the key dates.

Man-hour calculation:

It is the time required to carry out specific tasks.

Social costs:

They are paid in accordance with the legislation. They are incorporated in the company budget.

Building site costs:

Costs that are necessary for the company in order to perform their trade contracts (Storage sheds, sheds, field workshops, waste removal, working lights, health and safety precautions, special tools, tower crane, scaffolding, lifts…

Indirect costs:

Production, stores, distribution, marketing, administration. Costs related with the contract managers, foremen with fixed salary,..

Direct costs:

Expenses in connection with own production.

Suppliers and subcontractors fees:
An additional fee will be added to their tender bids. This fee covers administration and profit.

Contribution margin:

Expresses in percent how much profit the contractor wishes to make on their building project.

If the contractor wishes to make 15% profit on the project, then the direct and social costs will correspond to 85% of the final tender bid.

Once the calculation of own production is calculated and tender bids from subcontractors and suppliers have been received and accepted it is possible to begin the final calculation of the main contract. It includes:

- Tender bids subcontractors

- Building site arrangement and operation

- Costs of managing the main contract

- Site accommodation (IT, telephone, heating...)

- Security

- Winter precautions

CONTRACTING

- Negotiation

The client has the possibility of negotiating with the bidder:

Criteria A: lowest bid (the client is only allowed to negotiate with the lowest bidder)

Criteria B: The most economical advantageous (the client is allowed to negotiate with the top three lowest bids)

The client can ask to the lowest bid to present “COST SAVING MEASURES”.

- Contract legislation

Once the client has awarded the tender to a contractor a contract must be prepared.

The contract cannot include any new issues.

In accordance to AB92, the contractor shall provide security for the performance of his obligations towards the client. The bond provided shall correspond to 15% of the contract sum.

The contract specifies penalties.

If the contractors fails to submit the final account in due time, he loses his right to claim payment for extra wages and prices.

Once the main contractor has entered a contract with the client he has to enter contracts with subcontractor and accept bids from supplier.

- Insurances

The client has to pay for the usual fire and tempest insurance. The contractor must be included in the policy and he will be able to claim the insurance company directly in case of damage. (AB92)

It is the contractors responsibility to pay the insurance that covers accidental damages.

If the client takes an “all risks insurance” the contractor will be covered by the insurance.

STARTING UP

Before the start of the works, the project manager has to:

- Ensure that authority approval and permits have been issued

- Notification of commencement

- Enter agreements concerning the handling of waste

- Risk analysis

The risk assessment takes place before the start of the works.

- Building site inspection:

The project manager makes a personal inspection of the building site in order to get familiar with the site conditions and the surroundings.

Technical installations, access roads, welfare provisions, conditions with neighboring plots, traffic, cleaning, fencing, terrain conditions, must be observed.

- Process planning

Done by the main contractor in collaboration with the subcontractors.

- Manning and equipment plan

It is necessary to make a manning plan, partly as a part of “Plan for health and Safety plan” and partly to provide to the company an overview of which resources are busy during a given period of time.

- Setting out the building site

The setting out of the main grid lines and levels is responsibility of the client.

- Order and delivery plan

The trade contractor is responsible for preparing the orders and for the delivery plan.

The materials must be delivered at the site according to the needs.

Deliver plans help to create a regular flow of materials with few urgent orders, reduce storage needs at the building site, reduce material damage and waste, avoid accidents.

- Work place assessment

It is the responsibility of the individual trade contractor to write the work place assessment.

It includes a description of possible physical, mental, chemical, biological and ergonomic impacts as well as risks and accidents.

- Safety work

It is the client’s responsibility to appoint a coordinator to conduct the coordination of safety work during the construction (usually by one of the client’s consultant or the main contractor).

The coordination takes place in the safety meetings.

- Site meetings

Site meetings have the purpose to coordinate the own productions and subcontractor’s production.

- Quality assurance

The client in collaboration with the main contractor must approve a quality handbook.

Procedures for quality assurance must be identified in the handbook.

The main contractor makes a supervision plan for the subcontractor and for work in own production.

- Starting up meeting.

The main contractor calls for a starting up meeting immediately before the beginning of the works.

At this meeting documents relating to the project will be examined again and last minute questions will be answered.

CONSTRUCTION

The contractor takes care of registrations, applies for permits, asks for inspection and procures certificates. He also covers the costs that these involve.

The contractor bears the risk for all work until is handed over. He is also responsible for maintenance of work.

The client’s payment obligations appear in AB92.

Work must be carried out in accordance with the agreed time schedule. In case of delays there will be sanctions.

It is the project manager’s task to manage the building process.

It is recommended to arrange meetings: starting up meetings, site meetings and safety meetings.

- Control plans

The client defines his quality demands in the tender documents in the tender. During the starting up phase, and based on these plans, the contractor makes his own control plans for delivery control, process control and final control.

- Payments

Monthly interim certificates: by the end of each month, the contractor and the client calculate the total value of work carried out at the site. This amount is deducted the value of work already carried out and paid for. The difference corresponds to the value of the work performed during the month in question.

In case of overdue payment, the client has to pay interests.

HANDING OVER

The contractor informs the client about the time of completion of works.

The client sets a handing over meeting that has to take place within 10 workdays of the time indicated.

Before the handing over meeting, the contractor examines the work in order to establish possible essential defects.

In case essential defects are established during the handing over meeting, the work cannot be handed over (essential defect: it impedes occupation). The contractor has to rectify the defect and it will be a new handing over meeting. It will result in payment of penalties.

In cases where only minor defects are identified the client will keep part of the contract sum until the defects have been rectified.

Once the building project is handed over to the client, the responsibility for coordination of health and safety and the safety plan are also handed over.

Once the work is handed over the contractor’s security bond will be reduced to 10%.

For a period of 5 years after handing over the contractor responsibility to rectify the defects established after handing over. If the contractor does not rectify them, the client can do it and send him the bill.

Handing over with subcontractor

After handing over with the client, the handing over with the subcontractors must take place.

Final payment

Within 35 workdays of handing over, the main contractor has to submit the final accounts to the client.

1-5 years inspections

One year after handing over: inspection of the work.

Final inspection after 5 years of the handing over.